## Merit Project Communications
# | Communication | Medium | Delivery Date | Frequency | Description/Notes | Audience | Reviewer | Staff | Owner
1 | Project Team Communication | Meeting | Ongoing | Weekly | Weekly status meeting to discuss schedule, communications, actions, risks & issues | Project Team | Azri | Staff | Aiman
2a | Executive Sponsor Communication | PPT | Ongoing | Weekly | Weekly status report to executive sponsors for overview of the project progress | Executive Sponsors - Jensen Huang & Liang Hua | Azri | Staff | Ariff
2b | Executive Sponsor Communication | Meeting | Ongoing | Monthly | Monthly executive overview of the project progress | Executive Sponsors - Jensen Huang & Liang Hua | Azri | Staff | Aiman
3 | FORMAL: Stakeholder Communication (Royal Malaysia Police, Immigration Department of Malaysia, National Security Council) | Email | 2020-10-11 | Monthly | Monthly stakeholders overview of project progress | Inspector-General of Police, Chief Director Immigration Department of Malaysia & Head of National Security Council | Azri, Aiman | Staff | Haziq
4 | Merit Liaison & FDs roles & responsibility | Email | 18/11/2020 | One-time | Create list of responsibilities for merit liaisons (e.g. communicate appropriate information to supevisors, dept heads, AVP's etc.) | Merit Liaisons & all FDs | Haziq | Staff | Ariff
5 | Communication to departments regarding grade minimums. | Email | 30/11/2020 | One-time | Will include instructions on ways to notify employees. | Merit liaisons | Aiman | Staff | Haziq
6 | FORMAL: Merit percentage notification, range notification, basic merit guidelines (Merit Liaisons & all FDs) | Letter | 13/12/2020 | One-time | Same document as #5 but with a bit more data. | Merit Liaisons & all FDs | Azri, Aiman | Staff | Haziq
7 | FAQ's | Webpage | 2021-02-01 | One-time | Can't finish web page until we have clarification from on dates. | Civilians | Ariff | Staff | Aiman
8 | Create additional webpage content | Webpage | 17/2/2021 | One-time | Can't finish web page until we have clarification from on dates. | Civilians | Ariff, Izzuddin | Staff | Azri
9 | Can't finish web page until we have clarification from on dates. | Email | 2021-05-03 | One-time | All merit increases have been approved based on final submission of data. You may notify employees starting 1/3/2021 and after package date. | Merit Liaisons & all FDs | Ariff, Izzuddin | Staff | Azri
10 | Reminder emails to merit liaisons to return final spreadsheets | XLS | 2021-12-03 | Every 4 days until s/s returned | Mitigation for risk of late spreadsheets | Merit Liaisons & all FDs | None | Staff | Ariff